Activity 1: Create Project

- Create a blank project

- The project should be scheduled forward with project start date November 4

Activity 2: Create and Maintain Calendar

- Project team is in India and their working time is

  - Default working time is 9 am – 1 pm, 2 pm – 6 pm on all week days (Monday – Friday)

  - Second Saturday of every month should be working day, 9 am – 1 pm, 2 pm – 6 pm

  - November 19 is holiday

- By default, all new tasks should be scheduled as per India working time

Activity 3: Create Task Structure

- Display the project title as the top-level summary task

- All new tasks should be automatically scheduled

- Insert the below phases and tasks

- Topic

  - Research Competitors

  - Gap Analysis

- Publisher

  - Research Publishers

  - Discuss with Publishers

  - Finalize Publishers

- Chapters

  - Author Chapter 1

  - Author Chapter 2

  - Author Chapter 3

  - Author Chapter 4

  - Author Chapter 5

- Publish

  - Prepare Digital Format

  - Publish Online

  - Prepare Launch Email

  - Advertise Book Launch

- Enter the durations of the tasks

| Task Name | Duration |
| --- | --- |
| Research Competitors | 2 wks |
| Gap Analysis | 1 wk |
| Research Publishers | 2 wks |
| Discuss with Publishers | 1 wk |
| Finalize Publisher | 2 days |
| Author Chapter 1 | 4 days |
| Author Chapter 2 | 1 day |
| Author Chapter 3 | 8 days |
| Author Chapter 4 | 1 wk |
| Author Chapter 5 | 3 days |
| Prepare Digital Format | 4 days |
| Publish Online | 3 days |
| Prepare Launch Email | 1 day |
| Advertise Book Launch | 3 days |

- For periodic review of project progress, you need to insert milestones at the end of each phase, and one for the project completion

- Due to procurement process, the digital tools are available after December 21. So, Publish > Prepare Digital Format can start on or after December 21

- Project should be completed by January 8.

Link tasks

- Sequence the tasks in the below order

  - Topic phase

    - Research Competitors –FS->Gap Analysis –FS->Finalize Topic –FS-> Research Publishers

  - Publisher phase

    - Research Publishers –FS->Discuss with Publishers –FS-> Finalize Publishers –FS-> Author Chapter 1

  - Chapters

    - Author Chapter 1 –FS-> Author Chapter 2, Author Chapter 3

    - Author Chapter 2 –SS-> Author Chapter 4

    - Author Chapter 4 –FS-> Author Chapter 5

    - Author Chapter 3, Author Chapter 5 –FS-> Chapters Completed –FS-> Prepare Digital Format

  - Publish

    - Prepare Digital Format –FS-> Publish Online

    - Publish Online –FF->Prepare Launch Mail

    - Publish Online –FS-> Advertise Book Launch

    - Advertise Book Launch –FS-> Project Completed

- You foresee a risk in finalizing the publisher immediately after discussing with publisher, so set a wait time of 3 days between “Discuss with Publishers” and “Finalize Publisher” tasks

- You sense an opportunity to start chapter 5 before chapter 4 is completed. So, you start authoring of Chapter 5 by 3 days before Chapter 4 is completed.

- Highlight the critical tasks in RED color.

Activity 4: Insert Resources

- Based on the type of job, the following team members are finalized for this project

| Name | Cost | Roles |
| --- | --- | --- |
| Robert | Variable Fee: $5 / h | Commissioning Editor, Digital Publishing Editor |
| Kirk | Variable Fee: $5 / h | Chapter Writer |
| Jane | Variable Fee: $8 / h | Chapter Writer |
| Gopal | Variable Fee: $6 / h | Chapter Writer |
| Siva | Fixed Fee: $20 | Editorial Assistant, Marketing Manager |
| Prakash | Variable Fee: $8 / h | Marketing Manager, Digital Publishing Editor |

- Publishing software needs to be procured. The procurement cost is $25.

Activity 5: Assign resources, Optimization

- Assign the team members to the tasks as per the role

| Task Name | Role |
| --- | --- |
| Research Competitors | Commissioning Editor |
| Gap Analysis | Commissioning Editor |
| Research Publishers | Editorial Assistant |
| Discuss with Publishers | Editorial Assistant |
| Finalize Publishers | Digital Publishing Editor |
| Author Chapter 1 | Chapter Writer |
| Author Chapter 2 | Chapter Writer |
| Author Chapter 3 | Chapter Writer |
| Author Chapter 4 | Chapter Writer |
| Author Chapter 5 | Chapter Writer |
| Prepare Digital Format | Digital Publishing Editor + Editorial Assistant |
| Publish Online | Digital Publishing Editor |
| Prepare Launch Email | Marketing Manager + Chapter Writer |
| Advertise Book Launch | Marketing Manager + Commissioning Editor |